## Sheet2
SYSTEM NAME : |  | Discere: Online Quiz/Activity Management System
MEMBERS : |  | Bitayo, Brix C. | Bitayo
|  | Clarin, Jake R. | Clarin
|  | Paragoso, Yllana Mikhaila B. | Paragoso
STATUS : |  |  | Todo | 📋
|  |  | In-Progress | ⏳
|  |  | Done | ✅
|  |  | On-hold | ⏸️
[6 empty] | August |  |  |  | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December
ID | Tasks | Assignee | Date Started | Date Finished | Status | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
FRD & ERD PROGRESS
0.1 | Discere FRD | Bitayo, Clarin, Paragoso | 2024-08-25 | 2024-08-27 | ✅ | bar: August 5
0.2 | Discere ERD | Bitayo, Clarin, Paragoso | 2024-08-27 | 2024-08-28 | ✅ | bar: August 5
FIGMA UI/UX PROGRESS
1 | LOGIN / SIGN IN
1.1 | Creating UI | Clarin | 2024-09-04 | 2024-09-05 | ✅ | bar: August 5 to September 1
1.2 | Redesign UI/UX | Paragoso | 2024-09-05 | 2024-09-05 | ✅ | bar: August 5 to September 1
2 | REGISTRATION / SIGN UP
2.1 | Creating UI | Clarin | 2024-09-04 | 2024-09-05 | ✅ | bar: August 5 to September 1
2.2 | Redesign UI/UX | Paragoso | 2024-09-05 | 2024-09-05 | ✅ | bar: August 5 to September 1
3 | LANDING PAGE
3.1 | Home Page | Paragoso | 2024-09-01 | 2024-09-06 | ✅ | bar: August 5 to September 2
3.2 | About us Page | Paragoso | 2024-09-06 | 2024-09-08 | ✅ | bar: August 5 to September 2
3.3 | Contact Us Page | Paragoso | 2024-09-06 | 2024-09-08 | ✅ | bar: August 5 to September 2
4 | DASHBOARD
4.1 | Creating UI/UX | Clarin | 2024-09-04 | 2024-09-08 | ✅ | bar: August 5 to September 2
4.2 | Redesign UI/UX | Paragoso | 2024-09-28 | 2024-10-04 | ✅ | bar: August 5 to October 1
5 | FLASHCARD VIEW PAGE
5.1 | Creating UI | Bitayo, Clarin | 2024-09-07 | 2024-09-07 | ✅ | bar: August 5 to September 1
5.2 | Redesign UI/UX | Clarin | 2024-09-07 | 2024-09-08 | ✅ | bar: August 5 to September 2
5.3 | Redesign UI/UX | Paragoso | 2024-10-05 | 2024-10-11 | ✅ | bar: August 5 to October 2
6 | FLASCARD CREATION PAGE
6.1 | Creating UI/UX | Clarin | 2024-09-05 | 2024-09-08 | ✅ | bar: August 5 to September 2
6.2 | Remake UI/UX | Paragoso | 2024-10-05 | 2024-10-11 | ✅ | bar: August 5 to October 2
7 | QUIZ VIEW PAGE
7.1 | Creating UI | Bitayo, Clarin | 2024-09-07 | 2024-09-07 | ✅ | bar: August 5 to September 1
7.2 | Redesign UI/UX | Clarin | 2024-09-07 | 2024-09-08 | ✅ | bar: August 5 to September 2
8 | QUIZ CREATION PAGE
8.1 | Creating UI/UX | Clarin | 2024-09-05 | 2024-09-08 | ✅ | bar: August 5 to September 2
FRONTEND PROGRESS OVERVIEW
0.1 | GitHub Setup | Paragoso | 2024-09-22 | 2024-09-22 | ✅ | bar: August 5 to September 5
1 | LANDING PAGE
1.1 | Home Page | Clarin | 2024-10-17 | 2024-11-01 | ✅ | bar: August 5 to November 1
1.2 | About us Page | Clarin | 2024-10-19 | 2024-11-02 | ✅ | bar: August 5 to November 1
1.3 | Contact Us Page | Clarin | 2024-10-25 | 2024-10-31 | ✅ | bar: August 5 to October 5
1.3.1 | Send Query Function | Bitayo | 2024-11-05 | 2024-11-22 | ✅ | bar: August 5 to November 4
1.4 | Features Page | Clarin | 2024-10-27 | 2024-11-03 | ✅ | bar: August 5 to November 1
2 | USER AUTHENTICATION
2.1 | Login / Sign-in | Clarin | 2024-09-22 | 2024-10-13 | ✅ | bar: August 5 to October 3
2.1.1 | (UI/UX Design) Login / Sign-in | Clarin | 2024-09-22 | 2024-10-13 | ✅ | bar: August 5 to October 3
2.2 | Registration / Sign up | Bitayo | 2024-09-22 | 2024-09-22 | ✅ | bar: August 5 to September 5
2.2.1 | (UI/UX Design) Registration / Sign up | Clarin | 2024-09-22 | 2024-09-22 | ✅ | bar: August 5 to September 5
2.3 | Forget Password | Bitayo | 2024-10-14 | 2024-11-01 | ✅ | bar: August 5 to November 1
2.4 | Gmail Login | Bitayo | 2024-10-13 | 2024-10-13 | ✅ | bar: August 5 to October 3
3 | FLASHCARD CREATION & MANAGEMENT
3.1 | (UI/UX Design) Creation of Library Study Set Page | Paragoso | 2024-11-01 | 2024-11-03 | ✅ | bar: August 5 to November 1
3.1 | (UI/UX Design) Creation of Flashcard Creation Page | Clarin | 2024-10-14 | 2024-10-30 | ✅ | bar: August 5 to October 5
3.2 | CRUD for Flashcards | Clarin | 2024-10-14 | 2024-12-07 | ✅ | bar: August 5 to December 1
3.2.1 | (Create) Creating Flashcards | Clarin | 2024-10-14 | 2024-12-05 | ✅ | bar: August 5 to December 1
3.2.2 | (Read) Flashcard Display in Library | Clarin | 2024-11-23 | 2024-12-05 | ✅ | bar: August 5 to December 1
3.2.3 | (Update) Editing Existing Flashcard | Clarin | 2024-11-23 | 2024-12-07 | ✅ | bar: August 5 to December 1
3.2.3 | (Delete) Deleting Flashcard | Clarin | 2024-11-23 | 2024-12-06 | ✅ | bar: August 5 to December 1
3.4 | Merging Process of Dashboard and Flashcard | Clarin | 2024-11-16 | 2024-11-16 | ✅ | bar: August 5 to November 3
4 | FLASHCARD DECKS ORGANIZATION
4.1 | Create Decks | Clarin | 2024-11-14 | 2024-11-28 | ✅ | bar: August 5 to November 5
4.2 | Decks Display | Clarin | 2024-11-18 | 2024-11-29 | ✅ | bar: August 5 to November 5
4.2.1 | (UI/UX Refined Design) Decks Display | Clarin | 2024-11-24 | 2024-12-07 | ✅ | bar: August 5 to December 1
4.2.2 | Filter by Subjects | Clarin | 2024-12-07 | 2024-12-09 | ✅ | bar: August 5 to December 1
5 | QUIZ MANAGEMENT
5.1 | Creation Page of Library Exams Page | Paragoso | 2024-11-01 | 2024-11-03 | ✅ | bar: August 5 to November 1
5.1.1 | Quiz Creation Page 1 | Paragoso | 2024-11-01 | 2024-12-03 | ✅ | bar: August 5 to December 1
5.1.2 | Quiz Creation Page 2 | Paragoso | 2024-12-03 | 2024-12-07 | ✅ | bar: August 5 to December 1
6 | STUDY MODE
6.1 | Study Flashcards | Clarin | 2024-11-22 | 2024-12-07 | ✅ | bar: August 5 to December 1
7 | QUIZ MODE
7.1 | Take Quizzes | Paragoso | 2024-12-03 | 2024-12-10 | ✅ | bar: August 5 to December 2
7.2 | View Quiz Results | Paragoso | 2024-12-03 | 2024-12-10 | ✅ | bar: August 5 to December 2
8 | USER PROFILE MANAGEMENT (SETTINGS)
8.1 | Reads Username to Dashboard | Paragoso | 2024-10-14 | 2024-10-15 | ✅ | bar: August 5 to October 3
8.2 | User Profile Display | Paragoso | 2024-10-15 | 2024-10-15 | ✅ | bar: August 5 to October 3
8.3 | User Settings Page | Paragoso | 2024-11-18 | 2024-11-19 | ✅ | bar: August 5 to November 3
8.3.1 | Change/Upload User Profile Picture | Paragoso | 2024-10-15 | 2024-12-01 | ✅ | bar: August 5 to December 1
8.3.2 | Change First name, Last name | Bitayo | 2024-11-24 | 2024-12-07 | ✅ | bar: August 5 to December 1
8.3.3 | Change Email | Bitayo | 2024-11-24 | 2024-12-05 | ✅ | bar: August 5 to December 1
8.3.4 | Change Username | Bitayo | 2024-11-24 | 2024-12-02 | ✅ | bar: August 5 to December 1
8.3.5 | Change Password | Bitayo | 2024-11-24 | 2024-12-06 | ✅ | bar: August 5 to December 1
| Delete Account | Bitayo | 2024-11-24 | 2024-12-01 | ✅ | bar: August 5 to December 1

## Copy of Sheet2
System Name | Discere: Online Quiz/Activity Management System
Members: | Bitayo, Brix C.
Clarin, Jake R.
Paragoso, Yllana Mikhaila B.
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  |  | October
Tasks | Assignee | Date Started | Date Finished | Status | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
Discere FRD | Bitayo, Clarin, Paragoso | 2024-08-25 | 2024-08-27 | bar: August 5
Discere ERD | Bitayo, Clarin, Paragoso | 2024-08-27 | 2024-08-28 | bar: August 5
SYSTEM UI/UX DESIGN (FIGMA)
1. LOGIN / SIGN IN
Creating UI | Clarin | 2024-09-04 | 2024-09-05 | bar: September 1
Redesign UI/UX | Paragoso | 2024-09-05 | 2024-09-05
2. REGISTRATION / SIGN UP
Creating UI | Clarin | 2024-09-04 | 2024-09-05 | bar: September 1
Redesign UI/UX | Paragoso | 2024-09-05 | 2024-09-05
3. LANDING PAGE
Home Page | Paragoso | 2024-09-01 | 2024-09-06 | bar: September 1 to September 3; September 5
About us Page | Paragoso | 2024-09-06 | 2024-09-08 | bar: September 2 to September 3; September 5
Contact Us Page | Paragoso | 2024-09-06 | 2024-09-08 | bar: September 3 to September 4
Features Page | Paragoso
4. DASHBOARD
Creating UI/UX | Clarin | 2024-09-04 | 2024-09-08 | bar: September 1 to September 2
Redesign | Paragoso | 2024-09-28 | bar: September 5
5. FLASHCARD VIEW PAGE
Creating UI | Bitayo, Clarin | 2024-09-07 | 2024-09-07 | bar: September 1
Redesign UI/UX | Clarin | 2024-09-07 | 2024-09-08 | bar: September 1 to September 2
6. FLASCARD CREATION PAGE
Creating UI/UX | Clarin | 2024-09-05 | 2024-09-08 | bar: September 1 to September 2
7. QUIZ VIEW PAGE
Creating UI | Bitayo, Clarin | 2024-09-07 | 2024-09-07 | bar: September 1
Redesign UI/UX | Clarin | 2024-09-07 | 2024-09-08 | bar: September 1 to September 2
8. QUIZ CREATION PAGE
Creating UI/UX | Clarin | 2024-09-05 | 2024-09-08 | bar: September 1 to September 2
SYSTEM UI/UX FRONTEND
1. LOGIN / SIGN IN
Creating UI | Clarin | 2024-09-20 | 2024-09-22 | bar: September 3 to September 4
2. REGISTRATION / SIGN UP
Creating UI | Bitayo | 2024-09-20 | 2024-09-22 | bar: September 3 to September 4
3. LANDING PAGE
Creating UI
4. DASHBOARD
Creating UI
5. FLASHCARD VIEW PAGE
Creating UI
6. FLASCARD CREATION PAGE
Creating UI
7. QUIZ VIEW PAGE
Creating UI
8. QUIZ CREATION PAGE
Creating UI
SYSTEM FEATURES
GITHUB SETUP | Paragoso | 2024-09-22 | 2024-09-22 | bar: September 5
1. USER AUTHENTICATION
1.1 LOGIN / SIGN IN | Clarin | 2024-09-22 | bar: September 5
1.2 REGISTRATION / SIGN UP | Bitayo | 2024-09-22 | 2024-09-22 | bar: September 5
1.3 FORGET PASSWORD
1.4 GMAIL LOGIN
2. FLASHCARD MANAGEMENT
2.1 Flashcard Creation Page | Clarin
2.2 Flashcard Display | Clarin
3. QUIZ MANAGEMENT
4. STUDY MODE
5. QUIZ MODE
6. USER PROFILE MANAGEMENT
1. READS USER NAME TO DASHBOARD